## Risk Register
ENTERPRISE RISK REGISTER — GRC PORTFOLIO
ISO 27001:2022 · SOC 2 TSC · NIST CSF 2.0 · GDPR ¦ Owner: Johnbosco Okonkwo, CISSP · Risk Lead
Risk ID | Risk Name | Domain | Risk Description | Likelihood (1-5) | Impact (1-5) | Inherent Score | Severity | Residual Likelihood | Residual Impact | Residual Score | Residual Severity | Treatment Status | Risk Owner | Frameworks | Review Date | Trend | Treatment Plan | Last Updated
RSK-001 | Cloud Storage Misconfiguration | Cloud & Infrastructure | Improperly configured S3 buckets or Azure Blob Storage may expose sensitive customer data to the public internet. | 4 | 5 | 20 | Critical | 2 | 3 | 6 | Medium | Open | CISO | ISO 27001, SOC 2, NIST CSF | 2026-09-01 | ↑ | Implement automated config scanning. Enforce bucket ACLs and public access blocks. Monthly cloud security review. | 2026-08-01
RSK-002 | Third-Party Vendor Data Access | Third Party | Vendors with excessive access to production systems and customer data present significant supply chain risk. | 3 | 5 | 15 | High | 2 | 3 | 6 | Medium | Open | Vendor Manager | ISO 27001, SOC 2, GDPR | 2026-09-15 | → | Vendor risk tiering. Mandate DPA agreements for Tier 1 vendors. Deploy PAM for vendor sessions. | 2026-07-30
RSK-003 | Ransomware Attack on Core Systems | Information Security | Ransomware targeting critical systems could cause total data loss and GDPR Art.33 breach notification obligations. | 3 | 5 | 15 | High | 1 | 4 | 4 | Low | Mitigated | CISO | ISO 27001, SOC 2, NIST CSF, GDPR | 2026-10-01 | ↓ | EDR deployed across all endpoints. Immutable backups enforced. IR tabletop exercise completed Q1 2026. | 2026-06-01
RSK-004 | GDPR Non-Compliance — Data Retention | Compliance & Legal | Failure to enforce retention schedules risks holding PII beyond lawful purpose. Fines up to 4% of global turnover. | 3 | 4 | 12 | High | 2 | 3 | 6 | Medium | Open | DPO | GDPR, ISO 27001 | 2026-09-30 | → | Define retention schedules per data category. Automate deletion workflows. Update RoPA. | 2026-07-20
RSK-005 | Privileged Account Compromise | Information Security | Compromise of admin accounts through credential theft could allow full system access and data exfiltration. | 3 | 4 | 12 | High | 1 | 3 | 3 | Low | Mitigated | Head of Engineering | ISO 27001, SOC 2, NIST CSF | 2026-10-15 | ↓ | MFA enforced on all privileged accounts. JIT access deployed. Quarterly access reviews conducted. | 2026-06-15
RSK-006 | Business Email Compromise (BEC) | Information Security | Attackers impersonating executives via spoofed email to initiate fraudulent wire transfers or data exfiltration. | 4 | 4 | 16 | High | 2 | 2 | 4 | Low | Mitigated | CISO | ISO 27001, NIST CSF | 2026-10-01 | ↓ | DMARC p=reject enforced on all 12 domains. Quarterly phishing simulations. OOB wire transfer verification. | 2026-07-01
RSK-007 | Software Supply Chain Attack | Third Party | Malicious code injected into third-party libraries or open-source dependencies used in production software. | 2 | 5 | 10 | High | 1 | 4 | 4 | Low | Open | Head of Engineering | ISO 27001, SOC 2, NIST CSF | 2026-09-01 | ↑ | SBOM implementation for all production services. Snyk dependency scanning in CI/CD pipeline. | 2026-07-30
RSK-008 | Insider Threat — Data Exfiltration | Human Resources | Malicious or negligent insider copying sensitive data to unauthorised destinations, especially during offboarding. | 2 | 4 | 8 | Medium | 1 | 3 | 3 | Low | Accepted | HR Director | ISO 27001, SOC 2, GDPR | 2026-11-01 | → | DLP monitoring high-risk data movements. Offboarding checklist enforced. Access revoked within 1 hour of termination. | 2026-06-01
RSK-009 | DDoS Attack on Customer-Facing Services | Cloud & Infrastructure | Volumetric or application-layer DDoS attack causing service unavailability and SLA breaches. | 3 | 3 | 9 | Medium | 2 | 2 | 4 | Low | Transferred | CTO | ISO 27001, SOC 2 | 2026-12-01 | → | Cloudflare Enterprise DDoS protection. Financial risk transferred. Auto-scaling configured. | 2026-09-30
RSK-010 | Unpatched Critical Vulnerabilities | Information Security | Failure to patch CVEs with CVSS >= 9.0 within 24 hours per policy leaves systems exposed to known exploits. | 3 | 4 | 12 | High | 2 | 2 | 4 | Low | Mitigated | Head of Engineering | ISO 27001, SOC 2, NIST CSF, GDPR | 2026-09-15 | ↓ | Qualys scanner weekly scans. Patch SLAs: Critical 24hr, High 7 days, Medium 30 days. 94% patch compliance achieved. | 2026-05-15
RSK-011 | Inadequate Backup & Recovery Testing | Operational | Backups exist but recovery procedures are untested. Failure during an actual incident creates dangerous false assurance. | 2 | 5 | 10 | High | 1 | 3 | 3 | Low | Open | Head of Operations | ISO 27001, SOC 2 | 2026-09-01 | → | Quarterly restore tests for all Tier 1 systems. RTO/RPO targets defined. Results reported to CISO. | 2026-06-30
RSK-012 | Social Engineering & Phishing | Human Resources | Employees targeted via spear-phishing or vishing leading to credential disclosure or malware installation. | 4 | 3 | 12 | High | 2 | 2 | 4 | Low | Mitigated | CISO | ISO 27001, SOC 2, NIST CSF | 2026-10-01 | ↓ | Quarterly phishing simulations (KnowBe4). Mandatory annual security awareness training. 6% click rate achieved. | 2026-04-01

## Instructions
HOW TO ADD A NEW RISK TO THE REGISTER
Step 1 — Click on the first empty row (row 16) in the Risk Register tab
Step 2 — Type RSK-013 in column A, then fill each column across
Step 3 — Use the dropdown arrows for Domain, Status, Owner, Scores and Trend
Step 4 — Save the sheet (Ctrl+S or it auto-saves in Google Sheets)
Step 5 — Go to your dashboard and click the Refresh button
COLUMN REFERENCE GUIDE
A — Risk ID RSK-013, RSK-014 etc. (always sequential)
B — Risk Name Short descriptive name of the risk
C — Domain Dropdown: Information Security, Cloud, Third Party etc.
D — Description Full description of the risk scenario and threat source
E — Likelihood Dropdown 1-5: 1=Rare, 3=Possible, 5=Almost Certain
F — Impact Dropdown 1-5: 1=Minimal, 3=Moderate, 5=Catastrophic
G — Inherent Score Multiply E x F manually e.g. 4 x 5 = 20
H — Severity Dropdown: Critical(17-25), High(10-16), Medium(5-9), Low(1-4)
I — Residual Like Likelihood after controls applied
J — Residual Imp Impact after controls applied
K — Residual Score Multiply I x J manually
L — Residual Sev Dropdown: same scale as H
M — Status Dropdown: Open, Mitigated, Accepted, Transferred, Closed
N — Risk Owner Dropdown: person responsible for this risk
O — Frameworks ISO 27001, SOC 2, GDPR, NIST CSF (comma separated)
P — Review Date Next scheduled review date e.g. 2026-09-01
Q — Trend Dropdown: ↑ getting worse ↓ improving → stable
R — Treatment Description of controls implemented or planned
S — Last Updated Date this row was last updated e.g. 2026-08-13